## Slide 2: What is project?
A temporary endeavor undertaken to create a unique product, service, or result .
-Project Management Institute

## Slide 3: What is project management?
The application of knowledge, skills, tools, and techniques to project activities to meet the project requirements.

## Slide 4: Why project management is important?

## Slide 5
This is a work product or a group of work products. Work products produced for the customer are also called deliverables.
This is the work to be performed to achieve the outcome. The work is broken down into units of work, which can be tasks or activities. A task is the smallest amount of work that can be managed. Tasks and activities can also be recursively grouped into higher-level activities. Work is described in work packages.
A schedule maps on a timeline the units of work performed to achieve the outcome. Units of work can depend on each other. A schedule has a start, a duration, and an end.
The people (called participants), funds, equipment, and facilities required to perform the work are the project’s resources. People assume one or more roles in the project. Each role is responsible for one or more work packages.
Project components
Schedule
Work
Outcome
Resource

## Slide 6: Project management concepts
Tasks and activities
Work products, work packages, and Roles
Work breakdown structure
Task model
Skill Matrix
Software project management plan

## Slide 7
A task is a well-defined work assignment for a project participant or a team. A task is the
smallest unit of work that is subject to project management. A task includes a description and a
duration, and is assigned to a role filled by a participant. Tasks consume resources and produce one or more a work products. They often consume work products produced by other tasks
Activities are larger units of work. Their duration is often the same as a development phase, such as requirements analysis or system design. When activities span the whole duration of a project, they are called project functions. Examples of project functions are configuration management and project management itself.

## Slide 8: Task, Activities and project function (UML Class diagram)

## Slide 9: Work products, Work Packages, and Roles
A manager assigns tasks, activities, and project functions to participants or a team, who carry it out, while the manager monitors the progress and completion of the work.
In a small project this can be done informally, often with a shake of hands.
In larger projects, this must be spelled out more explicitly in form of a work package.

## Slide 10: Work Package
A work package describes the
work products to be produced,
the resources needed to perform the work
the expected duration,
dependencies on inputs, which are work products produced by other tasks as well as dependencies on other tasks.
It also specifies the acceptance criteria and the name of the responsible individual or organizational unit.
Deliverables – work products delivered to the customer
Internal work products

## Slide 11: Work breakdown structure (WBS)
The Work Breakdown Structure is the aggregation of all the work to be performed in a project.

## Slide 12: Task model
Tasks are related by temporal dependencies. The set of tasks and their dependencies is called the task model or network diagram.
Tasks have a duration, which corresponds to the actual time needed to complete the task given the number of required participants.
Durations are estimated by the project manager before the project starts. Once dependencies among tasks and task durations are known, the project manager can compute the shortest possible time in which the project can be completed.
This is simply the longest path in the task model, called critical path, that proceeds from the first task in the project to the last, where the length of the path is computed by adding the task durations.
The project manager focuses particularly on the tasks on the critical path, as any delay in these tasks results in delays of the overall project and missed deadlines.
A task’s slack time is the maximum amount of time a task can be postponed without delaying the rest of the project.
Time constraints can be used to specify the start or end of a task independent from the relationship of the task to other tasks. Time constraints are usually the result of an interaction of the project manager with the client.

## Slide 13: Skill Matrix
A skills matrix is a convenient form of relating the skills, knowledge, and interests of people to the tasks to be performed in the project.

## Slide 14: Software project management plan (SPMP)
The audience of the SPMP includes the management and the developers. The SPMP documents all issues related to client requirements (such as deliverables and acceptance criteria),the project goals, the project organization, the division of labor into tasks, and the allocation of resources and responsibilities.
In waterfall projects, this document is created before the project kick-off by the project manager.
In architecture-centric projects, it is created after the software architecture is defined.
In agile projects, this document is updated after each iteration.

## Slide 15: Software project management plan (SPMP)
Seven Sections
  The first three sections of the SPMP provide background information for the rest for the document. Contains hard constraints from the Project Agreement that are relevant to the developers.
  Project organization- communication roles, boundaries of each team and management, responsibilities assigned
  Managerial process plans- project initiation, steady state, and termination, and how it addresses unforeseen problems.
  Technical process plans, describes the technical standards that all teams are required to adopt.
  Supporting process plans, includes provisions for each of the supporting processes, such as configuration management, verification and validation, documentation, quality assurance, reviews and audits, problem reporting, subcontractor management, and process improvement.

## Slide 16: Software project management plan (SPMP)
The completed SPMP document should be reviewed both by management and by developers to ensure that the plans are feasible and realized in the project.

## Slide 17: Project management Activities
Planning
Organizing
Controlling
Terminating

## Slide 18: Classical Project Management
In classical projects, in the scope of the product is
relatively well defined at the beginning of the project and the goal of the project is to deliver within a specific deadline and budget.

## Slide 19: Classical Project Management-Planning
Defining the problem
Identifying the initial task models and organizing structure
Estimating needed resources such as personnel and funding

## Slide 20: Classical Project Management-Organizing
Setting up the communication infrastructure
Identifying skills
Assigning management roles
Assigning technical roles
Dealing with skill shortages
Selecting team sizes
Assembling the teams
Kick-off-meetings
Agreeing on the project scope

## Slide 21: Classical Project Management-Controlling
Meetings
  Periodic status meetings
  Sharp milestones
  Project reviews
  Code inspections
  Prototype demonstrations
Metrics
  Measuring financial status
  Measuring technical progress
  Measuring stability
  Measuring modularity
  Measuring maturity

## Slide 22: Classical Project Management-Controlling
Managing risks
The focus of risk management is to identify possible problems in the project and address them before they can significantly affect the delivery date or the budget. The key element of risk management is to set up the appropriate information flows such that risks and problems are accurately reported in a timely manner. Many projects fail either because simple problems were reported too late or because the wrong problem was addressed.
Four Categories
Likely, high potential impact
Unlikely, high potential impact
Likely, low potential impact
Unlikely, low potential impact.

## Slide 23: Classical Project Management-Terminating the project
Accepting the system
Installation
Postmortem

## Slide 24: Agile Project Management Activities

## Slide 26
Agile project management activities
Deal better with ill-defined requirements and emerging solution technologies, which are characterized by frequent changes

## Slide 27: Planning : Product backlog
Product backlog
Requirement 1
Requirement 2
Requirement 3
Kick off meeting

## Slide 28: Planning: Sprint backlog
Sprint planning meeting
Sprint backlog
Task 1
Task 2
Task 3

## Slide 29: Organizing : Scrum Roles

## Slide 30: Product owner
Responsible for the requirements
Participation in product backlog before each sprint.
Represents the client and user with a single voice.
Changes and re-prioritizes the product backlog before and after each sprint to reflect lesson learned.
Solely responsible for the product backlog and has no influence on the team during the sprint.
Hello I am a Product owner !
The most important part of the Scrum

## Slide 31: Scrum master
Management role responsible for the process
Sets up and enforces the rules and practices of the project
Facilitates daily Scrum meetings, monitor progress and removes obstacles.
Interface between Scrum team and product owner.
Ensure team productivity, and shields the team from distractions.
I am the Scrum master !

## Slide 32
Developing the product increment
Cross functional
Self organizing
No assigned role or job description
Participating in sprint planning meeting
Committing to the tasks defined in the sprint backlog
We are the team !

## Slide 34: Paper : Project Management Success Factors
Maybe the most beloved word of any project practitioner is “success”
project success
project management success
However, due to existence of many
different models of both project and project management success, it is hard to make a strong differentiation between them, mostly because of their mutual relationships.
How we can determine project success?
Although there is no consensus definition of what project success consists of ,authors are agreed that project success can be achieved through good actions of project manager

## Slide 35: Construction projects success is namely fundamental question for most of stockholder:
1- comprehensive literature review is given, defining different meanings and models of project management success through time.
2- project management success factors are given in a breakdown structure. The structure consists of three parts:
2-1 project management competence,
2-2 organizational elements
2-3 project management tools, methods, methodologies and techniques.
3- EU co-financed water projects
4- recommendations for future development are given.

## Slide 36: Project Management
Project management is:
planning,
organization,
monitoring and control of all aspects of project,
with motivation of all included to achieve project goals :
- on safe manner,
- within agreed schedule,
- within agreed budget
- within agreed performance criteria

## Slide 37
Namely, project can be successful despite unsuccessful project management because it has achieved higher and long-term goals.
In the moment when management of project stops, short-term orientation can be unsuccessful, but long-term outcome can be successful, because wider set of goals are satisfied, instead of narrow subset which project management consists of
The project main subjects are time, cost and quality.
The “iron triangle” model itself was the very first model of project management success.
Besides the “iron triangle”, and taking into account considerations of project management success, it is possible to find many different approaches: integration, scope, human resource, communication, risk and procurement management.

## Slide 38: How to measure if project management is successful?
Project management success can be evaluated through
already mentioned criteria of :
time,
cost,
quality,
scope,
resource
activity
models of measuring success like PMPA – Project Management Performance Assessment
maturity models of management within organization like Project Excellence Model.
But:
It is hard to answer the question of project management success evaluation precisely, because project management creates both tangible and intangible benefits
Project management success is one of the elements of project success, because the latter is hardly achievable without it

## Slide 39: project management parts which contribute the most, both to project management success and, consequently, to overall project success.
Elements of project management competence (C1)
Elements of organization (C2)
Elements of project management methodologies, methods, tools and techniques (C3)

## Slide 40
First category, elements of project management competence, consists of technical,
behavioral
contextual competencies
of project manager and project team members, as well as their coordination.
Second category, elements of organization, consists of:
organizational structure,
organizational culture,
organizational atmosphere
organization competence
Third category consists of :
project management methodologies,
project management software,
project management tools,
decision-making techniques,
risk assessment tools
information communication technology support tools.

## Slide 42: EU co-financed water projects: case study
EU co-financed water projects are public projects in the Republic of Croatia, which are being planned, selected, verified, monitored and controlled under Croatian water as Intermediate Body of Level 2. The fact that these projects are public, gives special accent on their project management. Project manager must take into consideration a larger scope of elements than time, cost and quality while taking managerial decisions – e.g. end users satisfaction, environment, health and safety, political and social implications etc.
Factors from the three categories will be tested on three case studies, whose characteristics can be seen in table 2

## Slide 43
Project managers were asked to assess the strength of project management competence (on Likert scale 1-5; where 1 = insufficient competence, 2 = sufficient competence, 3 = good competence, 4 = very good competence, 5 = excellent competence) and existence of organization competence, define parent organizations’ structure (functional, project or matrix), culture (clear or unclear, strong or weak, stabile or flexible, authoritative or democratic) and atmosphere (positive, neutral, negative) and name those project management methodologies, software, tools and techniques in use.

## Slide 44: The result of project reviews and interviews with project managers are shown in table 3

## Slide 46
Summery Of Table 3
Project managers on projects 1 and 2 are quite competent, especially in contextual sense
Project team’s competence on second project is excellent. Team members’ competence on the first project is very good,
and on the third project, very low.
Coordination between project manager and project team is extremely highly assessed on the second project, good
on the first project and bad on the third one.
All parent organizations have matrix structure, what means that some project team members work both on project
and in their regular departments of functional part of organization.
Speaking of organizational culture, it is stable in sense of years and tradition on operating on one way, but is strong and clear only on the second project.
Organizational atmosphere is negative only on the third project, which is not surprising according to the previous notions on that project.

## Slide 47
It is useful and purposeful to analyze organization competence only in those organizations that manage more than one project at the time, what is the case on the first and third project.
All elements of organization competence do exist on the first project, but not on the third one.
When it comes to the last category, it can be noted that first and second project are keen of usage of same project management methodologies, methods, tools and techniques. Third project, on contrary, uses only those tools that are obligatory on EU co-financed projects in water sector such as cost benefit analysis (including life cycle cost analysis, project chart, OBS and SWOT).
To conclude, second project has the most successful project management, the average one is on the first project and the worst on the third one.

## Slide 48: future PM development in praxes can be made, and they consist of:
Education. Education on PM competence and even more important
Relationship between project and parent organization. This relationship also defines project manager responsibilities in decision-making and, consequently, liability.
PM methodologies, methods, tools and techniques. It is very useful to know large scale of these, but only in order to help, not embitter yourself.

## Slide 49: Conclusion Part of Paper:
Project management is inevitable in today’s world
Project management is not only necessity for that improvement but also one field that seeks for improvement itself.
The project management success factors breakdown structure is illustrated.
Investments in project management field should be made, especially through strengthening people and organization competence.